AGREEMENT

THIS AGREEMENT IS

made as of the ____________ day of {_____________}, 20{___},

| between University: | THE REGENTS OF THE UNIVERSITY OF CALIFORNIA |
| --- | --- |
| whose address is: | {ADDRESS} |
| and Contractor: | {CONTRACTOR'S NAME} |
| whose address is: | {ADDRESS} |
| for the Project: | {PROJECT'S NAME} |
| University's Representative is: | {UNIVERSITY REP'S NAME} |
| whose address is: | {ADDRESS} |

University and Contractor hereby agree as follows:

ARTICLE 1 - THE WORK. Contractor shall provide all services, materials, tools, equipment, and labor required to perform and complete all work described in the Contract Documents (the "Work").

ARTICLE 2 - CONTRACT DOCUMENTS. {EDIT FOLLOWING LIST IF NEEDED. IF INFORMALLY BID, LEAVE AS IS. IF NEGOTIATED, DELETE Request for Bid & Bid Form. IF ADVERTISED, REPLACE "Request for Bid" W/ "Advertisement for Bids"}"Contract Documents" means Request for Bid, Bid Form, this Agreement, General Conditions, Supplementary Conditions, Exhibits, Specifications, {IF NO DRAWINGS, DELETE NEXT 4 WORDS} List of Drawings, Drawings, Addenda numbers _________, Notice to Proceed, Change Orders, and Notice of Completion.

ARTICLE 3 - THE CONTRACT SUM. Subject to the provisions of the Contract Documents, University will pay to Contractor, for the performance of the Work,  (the "Contract Sum").

ARTICLE 4 - CONTRACT TIME. Contractor shall commence the Work on the date specified in the Notice to Proceed and fully complete the Work within calendar days (the "Contract Time"). If Contractor is delayed in the completion of the Work by conditions beyond its control, a Change Order may be issued to make any necessary adjustment of the Contract Time. If the delay is an unreasonable delay caused by University, the Contract Sum may also be adjusted by Change Order.

ARTICLE 5 - LIQUIDATED DAMAGES. {IF USING LIQUIDATED DAMAGES, YOU MUST ALSO USE COMPENSABLE DELAY.   MAKE SURE LDs LANGUAGE IS INCLUDED IN THE SUPPLEMENTARY INSTRUCTIONS TO BIDDERS).  IF LESS <$50,000, DELETE TEXT AND STATE “Not Used”} If Contractor fails to complete the Work within the Contract Time, Contractor shall pay to University, as liquidated damages and not as a penalty, the sum of  for each day after the expiration of the Contract Time that the Work remains incomplete. After Substantial Completion, the rate for liquidated damages shall be reduced to the sum of  per day. University and Contractor agree that if the Work is not completed within the Contract Time, University's damages would be extremely difficult or impracticable to determine and that the aforesaid amount is a reasonable estimate of and a reasonable sum for such damages. University may deduct any liquidated damages due from Contractor from any amounts otherwise due to Contractor under the Contract Documents. This provision shall not limit any right or remedy of University in the event of any other default of Contractor other than failing to complete the Work within the Contract Time. This provision shall not be applicable nor act as a limitation upon University if Contractor abandons the Work. In such event, Contractor shall be liable to University for all losses and damages incurred by University.

ARTICLE 6 COMPENSABLE DELAY (IF USING LIQUIDATED DAMAGES, YOU MUST ALSO USE COMPENSABLE DELAY. USE AMOUNT ON BID FORM.  IF LESS <$50,000, DELETE

If Contractor is entitled to an increase in the Contract Sum as a result of a Compensable Delay, the Contract Sum will be increased by the sum of  per day for each day for which such compensation is payable.  A Compensable Delay is determined by whether the delay meets all of the following four conditions:  (1) the delay is critical and pushes Final Completion of the Work beyond the Contract Time, (2) within 7 days of the date the Contractor discovers an event or issue that may impact the critical path of the project, the Contractor submits a timely and complete Change Order Request, (3) the delay is not caused by a concealed, unforeseen or unknown condition except for a materially differing site condition, the financial inability, misconduct or default of the Contractor, a Subcontractor, or supplier, or the unavailability of materials or parts, and (4) the delay is caused by fire, strikes or obstructive actions by labor organizations, earthquake in excess of a magnitude of 3.5 on the Richter Scale, a materially differing site condition, an error or omission in the Contract Documents, a University-directed change in the scope of the work, or adverse weather on a scheduled work day,

THIS AGREEMENT is entered into by University and Contractor as of the date set forth above.

CONTRACTOR:			UNIVERSITY:

THE REGENTS OF THE

(Name of Firm)		UNIVERSITY OF CALIFORNIA

a 			UNIVERSITY OF CALIFORNIA, LOS ANGELES

(Type of Organization)

By: 			By:

(Signature)			(Signature)

(Printed Name)			(Printed Name)

(Title)			(Title)

California Contractor’s License(s):

(Name of Licensee)

(Classification and License Number)

(Expiration Date)

(Employer Identification Number)

Attach notary acknowledgment for all signatures of Contractor. If signed by other than the sole proprietor, a general partner or corporate officer, attach original notarized Power of Attorney or Corporate Resolution.